## README
Allen Jones — Departmental Goals WBS (2026)
Purpose
Two-lane prioritized work breakdown structure for Q3/Q4 2026 departmental goals.
Lane 1 = Training Redesign (pharmacy prototype + Docebo co-lead with Steph).
Lane 2 = Certification / Assessment (Team, Contractor, Pharmacy, FusionEHR, Client Ops).
CRITICAL ASSUMPTION — READ FIRST
Lane 1 pharmacy redesign (tasks 1.1.2 through 1.6.5) AND pharmacy assessment (tasks 2.4.1 through 2.4.4) are CONTINGENT on Kayla green-lighting the role-based redesign approach for pharmacy.
The pharmacy framework, Prescriber facilitator guide, learner packet, and pharmacy L1/L2 study guides sent to Kayla 6/14-6/15 were UNSOLICITED. Kayla has not yet given direction.
All contingent tasks are marked Status = 'Contingent' until Task 1.1.1 closes with a directional YES. If Kayla declines the redesign approach, Lane 1 spine collapses — see 'Contingency plan if Kayla declines' below for the fallback.
Decision point: next Allen + Kayla 1:1 (Mon 6/22, 2:00 PM ET).
Time budget
24 hours/week dedicated to departmental goals. Remaining time = client project management + ILT delivery.
Total period: Jun 16 - Dec 31, 2026 (~28 weeks).
Realistic availability: ~570 hours (after high-load weeks and holidays).
Planned effort total: see Capacity sheet (Total Planned column).
Sheets
Tasks — Full WBS with hierarchical IDs (1, 1.1, 1.1.1...), dates, effort, owners, dependencies.
Milestones — External client events + internal deadlines + escalation triggers.
Capacity — Weekly Allen-hours plan: available, planned per lane, variance.
Strategic framing baked into this plan
1. Pharmacy training redesign is the PROTOTYPE for role-based + cert work. IDHS Sept 14 is the proof point.
2. Honest scope cut: 2 pharmacy roles end-to-end by 9/14 (NOT all 5). Remaining 3 in Q4.
3. Honest scope cut: FusionEHR is the FIRST EHR cert built to proven pattern. Other EHR apps (eMAR, Order Mgr, CPOE, Lab Mgr) roll to Q1-Q2 2027.
4. Steph owns Docebo backend + LMS publishing + her existing 2026 app queue. Allen owns ID authorship + pattern enforcement.
5. Build Pattern doc (1.4) is mandatory scaffolding so Steph can pattern-match Allen's prototype without coaching.
6. Dom Davis is the bottleneck for Lane 2 EHR-side cert (L1/L2). Pharmacy SME review routes through Dylan/Isaac independently — not gated by Dom. Escalation trigger for Dom by EOW 6/19.
Goal-to-Owner mapping (per L&D Team Meeting deck 6/12)
Allen OWNS: Role-based EHR + cert (D), Team >=90% (F), Contractor cert (G), Client Ops cert co with Kayla T (I).
Allen CONTRIBUTES to but does NOT own: Docebo (Steph/Allen co), Pharmacy LMS suite (Steph), Pharmacy handoff (Kayla B), Async conversion (Steph).
Allen-owned tasks in this WBS span both lanes; co-contribution tasks are tagged in Owner column.
Tool conversion notes
MS Project: File > Open > select .xlsx. Map Outline Level column on import for hierarchy. Predecessors column uses WBS IDs.
Smartsheet: Import via File > Import > Microsoft Excel. Outline Level column drives parent-child indenting.
Claude-coded app: Tasks sheet is the source of truth. WBS ID is the unique key. Predecessors column is comma-separated WBS IDs (default Finish-to-Start).
Excel-only use: Use the outline level handles in the left margin to collapse/expand by lane and sub-workstream.
Column definitions (Tasks sheet)
WBS ID — Hierarchical identifier (1, 1.1, 1.1.1). Lane 1 starts with '1', Lane 2 with '2'.
Outline Level — 1=Lane parent, 2=Workstream parent, 3=Leaf task. Drives row indenting in compatible tools.
Lane — '1 - Training Redesign' or '2 - Certification'.
Task Name — Indented display; raw text is the actual name.
Predecessors — Comma-separated WBS IDs. Finish-to-Start dependency unless noted.
Start / Finish — ISO date format (YYYY-MM-DD). Working days assumed Mon-Fri.
Duration — Calculated via NETWORKDAYS formula (working days between Start and Finish).
Effort — Allen's hours only (excludes SME, Steph, contractor time).
Owner — Primary accountable party. Tasks where someone else leads but Allen contributes are noted.
Status — Not Started / In Progress / Waiting / Blocked / Complete / Decision Required / Contingent. "Contingent" = task depends on a pending decision (see Notes); "Decision Required" = a stakeholder owes a directional call. Update weekly.
Goal — Which 2026 L&D objective this feeds (Obj 1 / Obj 2 / Obj 3 / combinations).
Notes — Context, risks, decision points.
How to maintain
Update Status column weekly (Friday recap is the natural rhythm).
When a date slips, update Start / Finish; Duration auto-recalculates.
Re-validate Capacity sheet weekly — if Total Planned exceeds Available, scope must give before dates.
Re-cut WBS if: (a) Kayla rejects pharmacy framework, (b) Dom doesn't move within 2 more weeks, (c) IDHS Sept 14 date shifts, (d) new client wave drops.
Discussion prep for next Kayla 1:1
THE ASK: directional yes / no on the pharmacy role-based redesign approach. NOT detailed feedback on the 6/14-6/15 documents.
THE FRAMING: pharmacy redesign serves as the PROTOTYPE for the broader role-based + cert work across the EHR. IDHS Sept 14 is the natural proof point. FusionEHR Q4 is the first EHR application of the proven pattern.
HONEST SCOPE CUTS BAKED INTO THIS PLAN (flag these explicitly so Kayla is not surprised in November):
- 2 pharmacy roles end-to-end by IDHS 9/14 (not all 5). Remaining 3 in Q4.
- FusionEHR is the only EHR-side cert built in 2026. Other EHR apps (eMAR, Order Mgr, CPOE, Lab Mgr) roll to Q1-Q2 2027.
- 'Interactive, adult-learning-based modules' (Obj 3) delivered through prototype work, not a separate Docebo content rebuild.
THE TRADE: 8 scattered goal lines become 1 coherent program of work. Steph's queue stops competing with role-based reorg. Build Pattern doc (1.4) gives Steph something concrete to pattern-match against.
WHAT I AM NOT ASKING FOR: detailed feedback on the documents. That can wait until the directional call is made.
Contingency plan if Kayla declines the redesign approach
Lane 1 collapses to Workstream 1.7 (Docebo co-lead with Steph) only. ~210 hrs of planned Allen effort frees up.
Pharmacy LMS suite (Steph's Obj 1 goal) stays as her interactivity-pass work on existing content. Allen contributes ad-hoc only.
Pharmacy handoff (Kayla B's Obj 2 goal) continues — Allen does shadow -> co-deliver -> solo on EXISTING pharmacy training materials, not redesigned ones.
IDHS Sept 14 delivery uses existing pharmacy training materials. Still a proof point for the handoff goal, not for any redesign.
Freed hours redirect to additional EHR cert work in Lane 2 — likely eMAR and Order Manager certs in Q4 alongside FusionEHR, advancing Obj 1 'role-based packages for all EHR products' partially.
Worst-case impact: the 6/14-6/15 documents become reference material, not the spine of the year's program. Reusable for future cycles.
Best-case impact of the contingency: forces an explicit 'what is the Obj 3 deliverable' conversation that has been deferred.

## Tasks
WBS ID | Outline Level | Lane | Task Name | Predecessors | Start Date | Finish Date | Duration (days) | Effort (Allen hrs) | Owner | Status | Goal | Notes
1 | 1 | 1 - Training Redesign | LANE 1 — Training Redesign (Pharmacy prototype + Docebo co-lead) | [5 empty] | Allen | In Progress | Obj 1 + Obj 3 | Pharmacy = prototype; IDHS 9/14 = proof point; FusionEHR Q4 = first EHR application of pattern.
1.1 | 2 | 1 - Training Redesign | Pharmacy framework + IDHS scope lock | [5 empty] | Allen / Kayla | In Progress
1.1.1 | 3 | 1 - Training Redesign | Kayla GO/NO-GO decision on pharmacy redesign approach |  | 2026-06-15 | 2026-06-22 | 6 | 1 | Kayla (Allen flag) | Decision Required | Obj 1 | UNSOLICITED work sent 6/14-6/15: framework + Prescriber facilitator guide + learner packet + pharmacy L1/L2 study guides. Kayla has NOT given direction. The ask is a directional yes/no, NOT detailed feedback. Lane 1 pharmacy redesign (1.1.2-1.6.5) AND pharmacy assessment (2.4.x) are CONTINGENT on this decision. Decision point: next 1:1 (Mon 6/22).
1.1.2 | 3 | 1 - Training Redesign | Lock template per Kayla feedback | 1.1.1 | 2026-06-29 | 2026-07-02 | 4 | 6 | Allen | Contingent | Obj 1 | Lock structure: ILT redesign + facilitator guide + learner packet (Tip Guide replacement) + eLearning pre-req + JIT job aid.
1.1.3 | 3 | 1 - Training Redesign | Confirm IDHS Pilot Wave 1 roles attending |  | 2026-06-22 | 2026-06-26 | 5 | 2 | Allen + Steph | Not Started | Obj 1 | Determines minimum prototype scope. Likely Prescriber + 1 other (Pharmacist/Nurse). Ask Steph + Dylan.
1.1.4 | 3 | 1 - Training Redesign | Scope MVP: 2 roles E2E by 9/14, rest in Q4 | 1.1.2, 1.1.3 | 2026-06-29 | 2026-07-03 | 5 | 4 | Allen | Contingent | Obj 1 | Trade scope for quality: 2 roles fully built by IDHS, remaining 3 in Q4. Document the scope cut explicitly.
1.2 | 2 | 1 - Training Redesign | Pharmacy prototype — Role 1 (Prescriber, anchor) | 1.1.4 |  |  |  |  | Allen | Not Started |  | Anchor role — pattern emerges from this build.
1.2.1 | 3 | 1 - Training Redesign | ILT facilitator guide redesign — Prescriber | 1.1.4 | 2026-07-06 | 2026-07-24 | 15 | 18 | Allen | Contingent | Obj 1 | Build on 6/14 sample. Scenario-driven, decision-based, knowledge checks that surface job consequences.
1.2.2 | 3 | 1 - Training Redesign | Learner packet — Prescriber (Tip Guide replacement) | 1.2.1 | 2026-07-27 | 2026-08-07 | 10 | 12 | Allen | Contingent | Obj 1 | Replaces legacy Tip Guides. Job-aid format, role-aligned, workflow-anchored.
1.2.3 | 3 | 1 - Training Redesign | eLearning pre-req design + storyboard — Prescriber | 1.2.1 | 2026-07-27 | 2026-08-14 | 15 | 20 | Allen | Contingent | Obj 1 + Obj 3 | Parallel with 1.2.2. This is the Obj 3 'interactive, adult-learning-based module' deliverable.
1.2.4 | 3 | 1 - Training Redesign | JIT job aid design — Prescriber | 1.2.2 | 2026-08-03 | 2026-08-14 | 10 | 10 | Allen | Contingent | Obj 1 | Just-in-time micro-aids for at-workstation use during real work.
1.2.5 | 3 | 1 - Training Redesign | SME accuracy review — Prescriber (Dylan/Isaac) | 1.2.2, 1.2.3, 1.2.4 | 2026-08-17 | 2026-08-28 | 10 | 4 | Dylan/Isaac (Allen coord) | Contingent | Obj 1 | Pharmacy SMEs (Dylan/Isaac), NOT Dom. Independent of Dom queue.
1.2.6 | 3 | 1 - Training Redesign | Final revisions — Prescriber | 1.2.5 | 2026-08-31 | 2026-09-04 | 5 | 6 | Allen | Contingent | Obj 1
1.3 | 2 | 1 - Training Redesign | Pharmacy prototype — Role 2 (TBD: confirm at 1.1.3) | 1.1.4 |  |  |  |  | Allen | Not Started |  | Mirror Role 1 build, faster with pattern in hand.
1.3.1 | 3 | 1 - Training Redesign | ILT facilitator guide redesign — Role 2 | 1.2.1 | 2026-07-20 | 2026-08-07 | 15 | 14 | Allen | Contingent | Obj 1 | Lag Prescriber by ~2 weeks so pattern is established.
1.3.2 | 3 | 1 - Training Redesign | Learner packet — Role 2 | 1.3.1 | 2026-08-10 | 2026-08-21 | 10 | 10 | Allen | Contingent | Obj 1
1.3.3 | 3 | 1 - Training Redesign | eLearning pre-req design + storyboard — Role 2 | 1.3.1 | 2026-08-10 | 2026-08-28 | 15 | 16 | Allen | Contingent | Obj 1 + Obj 3
1.3.4 | 3 | 1 - Training Redesign | JIT job aid design — Role 2 | 1.3.2 | 2026-08-17 | 2026-08-28 | 10 | 8 | Allen | Contingent | Obj 1
1.3.5 | 3 | 1 - Training Redesign | SME accuracy review — Role 2 | 1.3.2, 1.3.3, 1.3.4 | 2026-08-31 | 2026-09-11 | 10 | 4 | Dylan/Isaac (Allen coord) | Contingent | Obj 1
1.3.6 | 3 | 1 - Training Redesign | Final revisions — Role 2 | 1.3.5 | 2026-09-08 | 2026-09-11 | 4 | 4 | Allen | Contingent | Obj 1
1.4 | 2 | 1 - Training Redesign | Build Pattern doc (scaffolding for Steph + future authors) | 1.2.1 |  |  |  |  | Allen | Not Started |  | Output layer (modules) + scaffolding layer (this). Without scaffolding, 'try to do things like Allen did' produces a polished user-manual dump.
1.4.1 | 3 | 1 - Training Redesign | Draft pattern structure (intro → scenario → KC → application → assessment) | 1.2.1 | 2026-07-27 | 2026-08-07 | 10 | 8 | Allen | Contingent | Obj 1 + Obj 3
1.4.2 | 3 | 1 - Training Redesign | Document decision rules (async vs ILT, scenario vs explanation) | 1.4.1 | 2026-08-10 | 2026-08-21 | 10 | 8 | Allen | Contingent | Obj 3
1.4.3 | 3 | 1 - Training Redesign | Annotated example walk-through using Prescriber as exemplar | 1.4.2, 1.2.6 | 2026-08-24 | 2026-09-04 | 10 | 6 | Allen | Contingent | Obj 3
1.5 | 2 | 1 - Training Redesign | IDHS Sept 14 proof point | 1.2.6, 1.3.6 |  |  |  |  | Allen | Not Started |  | Pharmacy handoff (Kayla B's Obj 2) lands here via prototype delivery.
1.5.1 | 3 | 1 - Training Redesign | Delivery prep & run-through | 1.2.6, 1.3.6 | 2026-09-08 | 2026-09-11 | 4 | 8 | Allen | Contingent | Obj 1 + Obj 2
1.5.2 | 3 | 1 - Training Redesign | IDHS Pilot Wave 1 delivery (pharmacy) | 1.5.1 | 2026-09-14 | 2026-09-18 | 5 | 30 | Allen | Contingent | Obj 1 + Obj 2 | 30 hrs delivery = pharmacy handoff proof. Counted as Lane 1 work this week, displaces other dept hours.
1.5.3 | 3 | 1 - Training Redesign | Post-delivery retro & pattern refinement | 1.5.2 | 2026-09-21 | 2026-09-25 | 5 | 6 | Allen | Contingent | Obj 1
1.6 | 2 | 1 - Training Redesign | Pharmacy remaining roles (Q4 build, post-proof) | 1.5.3 |  |  |  |  | Allen + Steph | Not Started |  | Roles 3-5 using proven pattern. Lighter effort/role.
1.6.1 | 3 | 1 - Training Redesign | Roles 3-5 build using proven pattern | 1.5.3 | 2026-09-28 | 2026-11-13 | 35 | 60 | Allen | Contingent | Obj 1
1.6.2 | 3 | 1 - Training Redesign | SME accuracy pass (remaining roles) | 1.6.1 | 2026-11-16 | 2026-11-27 | 10 | 6 | Dylan/Isaac (Allen coord) | Contingent | Obj 1
1.6.3 | 3 | 1 - Training Redesign | Steph publishes pharmacy modules to Docebo | 1.6.2 | 2026-11-30 | 2026-12-11 | 10 | 0 | Steph | Contingent | Obj 1 + Obj 3 | 0 hrs Allen — Steph builds from Allen's authored content per build pattern.
1.6.4 | 3 | 1 - Training Redesign | Allen QA on Steph's published modules | 1.6.3 | 2026-11-30 | 2026-12-11 | 10 | 8 | Allen | Contingent | Obj 3 | Pattern enforcement. Parallel with publish.
1.6.5 | 3 | 1 - Training Redesign | Pharmacy suite launch | 1.6.4 | 2026-12-14 | 2026-12-18 | 5 | 4 | Allen + Steph | Contingent | Obj 1 | Full pharmacy LMS suite live. Closes Steph's Obj 1 'Pharmacy LMS trainings' line.
1.7 | 2 | 1 - Training Redesign | Docebo co-lead with Steph (Obj 3 — Workstream A) | [5 empty] | Allen + Steph | Not Started |  | Steph leads backend (taxonomy, dashboards, publishing). Allen co-leads ID design + pattern enforcement.
1.7.1 | 3 | 1 - Training Redesign | Current-state audit — role gap mapping contribution |  | 2026-06-22 | 2026-07-03 | 10 | 4 | Allen | Not Started | Obj 3 | Steph back from HI week of 6/22. Allen contributes role-gap analysis; Steph handles inventory + usage data.
1.7.2 | 3 | 1 - Training Redesign | Role-based taxonomy design with Steph | 1.7.1, 1.1.2 | 2026-07-06 | 2026-07-24 | 15 | 10 | Allen + Steph | Not Started | Obj 3 | Lock taxonomy before Steph's FusionEHR build starts (8/21). Otherwise FusionEHR gets retrofitted later.
1.7.3 | 3 | 1 - Training Redesign | Pattern enforcement — FusionEHR build review (Steph) | 1.7.2, 1.4.3 | 2026-08-17 | 2026-08-21 | 5 | 4 | Allen | Not Started | Obj 3 | First Steph build using new pattern. Spot-check + redirect if needed.
1.7.4 | 3 | 1 - Training Redesign | Ongoing build pattern reviews (eMAR, Order Mgr, CPOE, Lab Mgr) | 1.7.3 | 2026-09-28 | 2026-12-31 | 69 | 12 | Allen | Not Started | Obj 3 | Rolling: eMAR ~10/2, Order Mgr ~11/6, CPOE ~12/4, Lab Mgr ~1/1/27. 3 hrs per review.
2 | 1 | 2 - Certification | LANE 2 — Certification / Assessment | [5 empty] | Allen | In Progress | Obj 2 | EHR cert program is the spine. Team / Contractor / Pharmacy / Client Ops are deployments to populations.
2.1 | 2 | 2 - Certification | EHR L1+L2 study guide & cert program design | [5 empty] | Allen + Dom | In Progress |  | Load-bearing for all of Lane 2 — every downstream deployment uses this design.
2.1.1 | 3 | 2 - Certification | Dom SME review of L1 + L2 (waiting + escalation if needed) |  | 2026-06-16 | 2026-07-03 | 14 | 2 | Dom (Allen monitor) | Waiting | Obj 2 | L1 with Dom ~13 days no movement. L2 added 6/16. ESCALATE TO KAYLA if no response by EOW 6/19.
2.1.2 | 3 | 2 - Certification | Incorporate Dom feedback into L1 + L2 | 2.1.1 | 2026-07-06 | 2026-07-17 | 10 | 12 | Allen | Not Started | Obj 2
2.1.3 | 3 | 2 - Certification | Lock cert program structure (scoring, retake, renewal policy) | 2.1.2 | 2026-07-20 | 2026-07-31 | 10 | 8 | Allen + Kayla + Adam | Not Started | Obj 2 | Define 'Phase 1' bar for both G (contractor) and I (Client Ops) so year-end measurement is unambiguous.
2.2 | 2 | 2 - Certification | Team product knowledge ≥90% (target 8/31) | 2.1.3 |  |  |  |  | Allen + Kayla | Not Started |  | Tracker reads 'End Q2' — confirm extension to 8/31.
2.2.1 | 3 | 2 - Certification | Team enrollment & comms | 2.1.3 | 2026-07-27 | 2026-07-31 | 5 | 2 | Allen | Not Started | Obj 2
2.2.2 | 3 | 2 - Certification | Team study window | 2.2.1 | 2026-08-03 | 2026-08-14 | 10 | 0 | L&D team self-study | Not Started | Obj 2 | 0 hrs Allen.
2.2.3 | 3 | 2 - Certification | Assessment delivery + scoring | 2.2.2 | 2026-08-17 | 2026-08-21 | 5 | 4 | Allen | Not Started | Obj 2
2.2.4 | 3 | 2 - Certification | Remediation for anyone <90% (cohort retake) | 2.2.3 | 2026-08-24 | 2026-08-28 | 5 | 4 | Allen | Not Started | Obj 2 | Aug 31 deadline. If Dom slips and 2.1.x compresses, F target is the first to break.
2.3 | 2 | 2 - Certification | Contractor cert Phase 1 (Q3 + rolling pre-assignment) | 2.1.3 |  |  |  |  | Allen + Kayla B | In Progress |  | Rolling: 100% certified before each contractor's first Q3 assignment.
2.3.1 | 3 | 2 - Certification | Q3 contractor-to-assignment map (RI DOC 6/29, DC DYRS 7/27, IL DOC SU 8/17, IDHS 9/14) |  | 2026-06-22 | 2026-06-26 | 5 | 3 | Allen + Kayla B + Adam | Not Started | Obj 2 | Critical visibility task. Raise at tomorrow's L&D Weekly. Connects to AB Staffing risk on Pharmacy Adoption slide.
2.3.2 | 3 | 2 - Certification | Pre-Phase-1 exception decisions (e.g., RI DOC Maurice 6/29) | 2.3.1 | 2026-06-22 | 2026-06-26 | 5 | 1 | Allen + Kayla | Not Started | Obj 2 | Maurice delivers RI DOC week of 6/29 — too early for Phase 1 cert. Decide: carve-out or scope shifts forward.
2.3.3 | 3 | 2 - Certification | Contractor cert curriculum design (uses 2.1 outputs) | 2.1.3 | 2026-07-06 | 2026-07-24 | 15 | 16 | Allen | Not Started | Obj 2
2.3.4 | 3 | 2 - Certification | Cohort 1 — DC DYRS contractors (cert before 7/27) | 2.3.3 | 2026-07-13 | 2026-07-24 | 10 | 8 | Allen + contractors | Not Started | Obj 2 | Compressed window. May need accelerated cert or exception.
2.3.5 | 3 | 2 - Certification | Cohort 2 — IL DOC SU contractors (cert before 8/17) | 2.3.3 | 2026-07-27 | 2026-08-14 | 15 | 8 | Allen + contractors | Not Started | Obj 2
2.3.6 | 3 | 2 - Certification | Cohort 3 — IDHS contractors incl. AB Staffing (cert before 9/14) | 2.3.3 | 2026-08-17 | 2026-09-11 | 20 | 8 | Allen + contractors | Not Started | Obj 2 | Addresses AB Staffing (Bricen, Jason) risk on Pharmacy Adoption slide.
2.3.7 | 3 | 2 - Certification | Phase 1 launch package documented | 2.3.4, 2.3.5, 2.3.6 | 2026-09-14 | 2026-09-25 | 10 | 4 | Allen | Not Started | Obj 2 | Curriculum + assessment + attestation tracker. Closes G goal by 9/30.
2.4 | 2 | 2 - Certification | Pharmacy assessment (cert tied to prototype) | 1.1.4, 2.1.3 |  |  |  |  | Allen + Dylan/Isaac | In Progress |  | Pharmacy study guides L1/L2 sent 6/15 (CIPS, CIPS Remote, sMARt). SME review = Dylan/Isaac (Pharmacy Support), NOT Dom.
2.4.1 | 3 | 2 - Certification | Pharmacy L1/L2 study guides SME review (Dylan/Isaac) |  | 2026-06-22 | 2026-07-17 | 20 | 4 | Dylan/Isaac (Allen coord) | Contingent | Obj 2 | Pharmacy guides sent 6/15 to Kayla. Routes through Dylan/Isaac as pharmacy SMEs, NOT Dom (Dom = EHR-side curriculum review). Independent of Dom queue — can move in parallel.
2.4.2 | 3 | 2 - Certification | Pharmacy cert structure decision (sub-cert under EHR? or standalone?) | 2.1.3 | 2026-08-03 | 2026-08-14 | 10 | 6 | Allen + Kayla | Contingent | Obj 2
2.4.3 | 3 | 2 - Certification | Pharmacy assessment build (per role) | 2.4.1, 2.4.2 | 2026-08-17 | 2026-09-04 | 15 | 12 | Allen | Contingent | Obj 2
2.4.4 | 3 | 2 - Certification | IDHS Pilot cert delivery (alongside ILT 9/14) | 2.4.3, 1.5.1 | 2026-09-14 | 2026-09-18 | 5 | 4 | Allen | Contingent | Obj 1 + Obj 2 | Cert assessment runs alongside the prototype delivery.
2.5 | 2 | 2 - Certification | Role-based EHR cert — FusionEHR (first EHR application) | 1.5.3, 2.1.3 |  |  |  |  | Allen | Not Started |  | Honest scope cut: FusionEHR cert by Q4. Remaining EHR apps (eMAR, OM, CPOE, Lab) roll into Q1-Q2 2027.
2.5.1 | 3 | 2 - Certification | FusionEHR role mapping (using proven pharmacy pattern) | 1.5.3 | 2026-09-22 | 2026-10-02 | 9 | 8 | Allen | Not Started | Obj 1 + Obj 2
2.5.2 | 3 | 2 - Certification | FusionEHR cert curriculum design | 2.5.1 | 2026-10-05 | 2026-10-30 | 20 | 24 | Allen | Not Started | Obj 1 + Obj 2
2.5.3 | 3 | 2 - Certification | FusionEHR cert assessment build | 2.5.2 | 2026-11-02 | 2026-11-20 | 15 | 16 | Allen | Not Started | Obj 1 + Obj 2
2.5.4 | 3 | 2 - Certification | FusionEHR cert launch (Q4 milestone — Obj 1 + Obj 3 hit) | 2.5.3 | 2026-12-01 | 2026-12-11 | 9 | 8 | Allen + Kayla | Not Started | Obj 1 + Obj 2
2.6 | 2 | 2 - Certification | Internal Client Ops cert Phase 1 (co with Kayla T) | 2.1.3 |  |  |  |  | Allen + Kayla T + Adam | Not Started |  | Target ≥90% Client Ops certified by Q4 end.
2.6.1 | 3 | 2 - Certification | Client Ops curriculum design (uses pharmacy + FusionEHR outputs) | 1.5.3, 2.5.1 | 2026-09-21 | 2026-10-30 | 30 | 16 | Allen + Kayla T | Not Started | Obj 2
2.6.2 | 3 | 2 - Certification | Adam coordination — Client Ops roster + enrollment plan | 2.6.1 | 2026-10-05 | 2026-10-16 | 10 | 4 | Allen + Adam | Not Started | Obj 2
2.6.3 | 3 | 2 - Certification | Phase 1 launch to Client Ops | 2.6.2 | 2026-10-19 | 2026-10-30 | 10 | 4 | Allen + Kayla T | Not Started | Obj 2
2.6.4 | 3 | 2 - Certification | Completion drive (Kayla T leads, Allen support) | 2.6.3 | 2026-11-02 | 2026-12-11 | 30 | 8 | Kayla T + Allen | Not Started | Obj 2
2.6.5 | 3 | 2 - Certification | ≥90% Client Ops certified — verification (Q4 milestone) | 2.6.4 | 2026-12-14 | 2026-12-30 | 13 | 4 | Allen | Not Started | Obj 2
[7 empty] | TOTAL | 511
Formulas:
Duration (days) = NETWORKDAYS([Start Date],[Finish Date])

## Milestones
Type | Name | Date | Lane / Goal | Allen Role | Notes
External - Client | RI DOC vILT (Maurice delivers, Allen prep support) | 2026-06-29 | Client work | Support | Maurice access: UAT (Rachel), LMS (via Steph/Allen as backup), agenda confirm (Kayla/Rachel).
Internal - Decision | Kayla framework decision deadline | 2026-06-26 | Lane 1 - Obj 1 | Awaiting | Sent Sun 6/14. Allen check-in at 1:1.
Internal - Decision | Q3 contractor-to-assignment map locked | 2026-06-26 | Lane 2 - Obj 2 | Lead | Without this, 'cert before assignment' rolling deadline is invisible.
Internal - Escalation | Dom L1+L2 review status (escalate if no movement) | 2026-06-19 | Lane 2 - Obj 2 | Escalate | L1 with Dom ~13 days as of 6/16. If silent by EOW, raise to Kayla.
External - Client | DC DYRS vILT (5 apps x 3 hrs, Allen delivers) | 2026-07-27 | Client work | Deliver | Compliance Mgr, Non/Formulary Mgr, Group Notes, Care Plans. 7/27-31. Contractors assigned must be Cohort 1 cert'd.
Internal - Deadline | Cohort 1 contractor cert complete (DC DYRS) | 2026-07-24 | Lane 2 - Obj 2 | Lead
External - Client | IL DOC Super User vILT (Centurion lead, tentative) | 2026-08-17 | Client work | Coord | Aug 17-21. Cohort 2 contractor cert must be complete before. Allen role depends on Centurion takeover.
Internal - Deadline | Cohort 2 contractor cert complete (IL DOC SU) | 2026-08-14 | Lane 2 - Obj 2 | Lead
Internal - Deadline | Team product knowledge >=90% target | 2026-08-31 | Lane 2 - Obj 2 | Lead | PATH 2 FIRST HARD DEADLINE. Gates: 2.1.1 (Dom) -> 2.1.2 -> 2.2.x sequence.
Internal - Deadline | Cohort 3 contractor cert complete (IDHS) | 2026-09-11 | Lane 2 - Obj 2 | Lead | Includes AB Staffing (Bricen, Jason).
External - Client | IDHS Pilot Wave 1 Training (pharmacy prototype proof point) | 2026-09-14 | Lane 1 - Obj 1 + Obj 2 | Deliver | 9/14-9/18 training; 9/21-9/25 go-live. Both prototype delivery AND pharmacy handoff proof for Kayla B's goal.
External - Client | IL DOC Wave 2 EUT (Centurion lead) | 2026-09-14 | Client work | Coord | 9/14-10/16, 5 weeks. Centurion delivers.
Internal - Deadline | Q3 close — Contractor Cert Phase 1 documented | 2026-09-30 | Lane 2 - Obj 2 | Lead
Internal - Deadline | Q3 close — Pharmacy handoff (Kayla B's goal) | 2026-09-30 | Lane 1 - Obj 2 | Deliver | Proof point = IDHS 9/14 delivery.
Internal - Deadline | Q3 close — Docebo reorg / role-based paths / interactive modules (Obj 3) | 2026-09-30 | Lane 1 - Obj 3 | Co-lead | Honest scope cut: pharmacy prototype + Prescriber/Role 2 modules count toward 'interactive adult-learning modules.' Full reorg by 9/30 is Steph's lane.
External - Client | IL DOC Go-Live (Big Bang) | 2026-10-19 | Client work | Support | High-load week.
External - Client | CO DOC Pilot EUT (Steph) | 2026-10-05 | Client work (Steph) | Awareness | 10/5-9. Steph delivers.
External - Client | CO DOC Big Bang EUT (Steph) | 2026-11-02 | Client work (Steph) | Awareness | 11/2-6. Steph delivers.
US Holiday | Thanksgiving week (reduced capacity) | 2026-11-26 | All | N/A | Week of 11/23 ~12 hrs available.
Internal - Deadline | FusionEHR cert launch | 2026-12-11 | Lane 2 - Obj 1 + Obj 2 | Lead | First EHR-side cert built to proven pattern.
Internal - Deadline | Pharmacy LMS suite launch (Steph's Obj 1 goal) | 2026-12-18 | Lane 1 - Obj 1 | Co-lead | Full pharmacy suite live.
Internal - Deadline | Client Ops Cert >=90% verified | 2026-12-30 | Lane 2 - Obj 2 | Lead
US Holiday | Christmas / New Year (reduced capacity) | 2026-12-24 | All | N/A | Weeks of 12/21 and 12/28 reduced.
Internal - Deadline | Q4 close — all in-scope goals | 2026-12-31 | All | Lead

## Capacity
Week Start (Mon) | Week End (Fri) | Allen Available Hrs | Lane 1 Planned | Lane 2 Planned | Total Planned | Variance (Avail - Planned) | Notes / Constraints
2026-06-15 | 2026-06-19 | 24 | 1 | 2 | 3 | 21 | Current week. Mostly waiting on Kayla framework + Dom L1. Steph LMS backup ad-hoc.
2026-06-22 | 2026-06-26 | 24 | 6 | 4 | 10 | 14 | Steph back. IDHS scope confirm, contractor map, Docebo audit support.
2026-06-29 | 2026-07-03 | 12 | 6 | 0 | 6 | 6 | RI DOC vILT week. Allen support only; Maurice delivers. Lock framework template, scope MVP.
2026-07-06 | 2026-07-10 | 24 | 14 | 8 | 22 | 2 | Prescriber ILT redesign begins, Dom feedback incorporation, taxonomy design with Steph.
2026-07-13 | 2026-07-17 | 24 | 12 | 14 | 26 | -2 | Heavy Prescriber build + Cohort 1 contractor cert delivery.
2026-07-20 | 2026-07-24 | 24 | 14 | 8 | 22 | 2 | Role 2 ILT begins, Prescriber wraps, lock cert program structure.
2026-07-27 | 2026-07-31 | 8 | 8 | 6 | 14 | -6 | DC DYRS vILT (15 hrs delivery, not in dept hrs). Cohort 2 cert begins.
2026-08-03 | 2026-08-07 | 24 | 14 | 6 | 20 | 4 | Prescriber learner packet + eLearning storyboard, Role 2 ILT, pharmacy cert structure.
2026-08-10 | 2026-08-14 | 24 | 16 | 6 | 22 | 2 | Heavy Role 2 + Prescriber JIT, Pattern doc decision rules. Team study window (self-study).
2026-08-17 | 2026-08-21 | 8 | 8 | 12 | 20 | -12 | IL DOC SU week (tentative attendance). Team assessment delivery, FusionEHR Steph build review.
2026-08-24 | 2026-08-28 | 24 | 14 | 8 | 22 | 2 | SME reviews, Team remediation, pattern doc walkthrough.
2026-08-31 | 2026-09-04 | 24 | 16 | 4 | 20 | 4 | Final revisions Roles 1+2, pattern doc complete. F deadline 8/31.
2026-09-07 | 2026-09-11 | 24 | 14 | 8 | 22 | 2 | IDHS prep + run-through, Cohort 3 cert wraps.
2026-09-14 | 2026-09-18 | 0 | 30 | 4 | 34 | -34 | IDHS Pilot DELIVERY (pharmacy prototype proof). Dept work paused.
2026-09-21 | 2026-09-25 | 24 | 10 | 8 | 18 | 6 | Post-delivery retro + FusionEHR mapping + Client Ops curriculum begins. IL DOC EUT begins (Centurion).
2026-09-28 | 2026-10-02 | 24 | 12 | 8 | 20 | 4 | Pharmacy remaining roles build begins. Q3 close. FusionEHR mapping wraps.
2026-10-05 | 2026-10-09 | 24 | 12 | 10 | 22 | 2 | FusionEHR cert curriculum design begins. CO DOC Pilot (Steph).
2026-10-12 | 2026-10-16 | 24 | 12 | 10 | 22 | 2 | FusionEHR cert continues. IL DOC EUT wraps 10/16.
2026-10-19 | 2026-10-23 | 12 | 8 | 8 | 16 | -4 | IL DOC Big Bang week. Client Ops Phase 1 launch.
2026-10-26 | 2026-10-30 | 24 | 12 | 10 | 22 | 2 | Recovery. Pharmacy roles continue, FusionEHR curriculum wraps.
2026-11-02 | 2026-11-06 | 24 | 12 | 10 | 22 | 2 | FusionEHR assessment build. CO DOC Big Bang (Steph).
2026-11-09 | 2026-11-13 | 24 | 12 | 10 | 22 | 2 | Pharmacy roles build wraps. FusionEHR assessment continues.
2026-11-16 | 2026-11-20 | 24 | 8 | 12 | 20 | 4 | SME pass on pharmacy roles, FusionEHR assessment wraps.
2026-11-23 | 2026-11-27 | 12 | 6 | 4 | 10 | 2 | Thanksgiving week (Thu/Fri off). Light work.
2026-11-30 | 2026-12-04 | 24 | 10 | 12 | 22 | 2 | Pharmacy QA + Steph publishing. FusionEHR cert launch prep.
2026-12-07 | 2026-12-11 | 24 | 10 | 16 | 26 | -2 | FusionEHR cert LAUNCH. Pharmacy QA continues. Client Ops completion drive.
2026-12-14 | 2026-12-18 | 24 | 6 | 10 | 16 | 8 | Pharmacy suite LAUNCH. Client Ops verification kicks off.
2026-12-21 | 2026-12-25 | 12 | 4 | 4 | 8 | 4 | Christmas week. Most folks PTO.
2026-12-28 | 2026-12-31 | 8 | 0 | 8 | 8 | 0 | Year-end. Client Ops >=90% final verification.
TOTAL |  | 576 | 307 | 230 | 537 | 39